## Milestone Tracker
Table 1 | Ensure you update in same format (e.g., 50% should be 0.50)
ActivityID | Milestone Name | Milestone Weight | Task Completion % | Completion % (by weight) | Overal Cummulative Completion % | StartDate | EndDate | OverallStatus | Owner | Comments
1 | Dev (Phase 1) | 0.15 | 0.75 | 0.1125 | 0.1125 | 2026-01-01 | 2026-01-30 | In Progress | Ryoma |  | Status
2 | Legal & Contracts | 0.05 | 0.5 | 0.025 | 0.1375 | 2026-01-14 | 2026-01-20 | In Progress | Heman |  | Not Started
3 | Collaboration Meetings | 0.05 | 0.8 | 0.04 | 0.1775 | 2026-01-21 | 2026-02-15 | In Progress | Heman |  | In-Progress
4 | Dev (Phase 2) | 0.2 | 0.66 | 0.132 | 0.3095 | 2026-02-01 | 2026-02-15 | In Progress | Ryoma |  | Pending
5 | Website Updates | 0.18 | 0.5 | 0.09 | 0.3995 | 2026-01-21 | 2026-02-21 | In Progress | Akshay |  | Completed
6 | Marketing & Ad Plan | 0.17 | 0.5 | 0.085 | 0.4845 | 2026-01-21 | 2026-02-21 | In Progress | Heman
7 | UAT & Security | 0.15 | 0 | 0 | 0.4845 | 2026-02-01 | 2026-02-28 | Not Started | Akshay
8 | Pilot (Go-Live) | 0 | 0 | 0 | 0.4845 | 2026-03-01 | 2026-04-30 | Not Started | Heman
9 | Product Metrics | 0.05 | 0 | 0 | 0.4845 | 2026-03-01 | 2026-05-31 | Not Started | Ryoma
10 | Production (Go-Live) | 0 | 0 | 0 | 0.4845 | 2026-06-01 | 2027-06-01 | Not Started | Heman

## Activity Tracker
Table 2 | Update the Current Status & Comments
TaskID | ActivityID | Milestone Name | Task Name | Status | Owner | End Date | Priority | Current Date | Comments
101 | 1 | Dev (Phase 1) | Bank Feed API Connection (Basiq) & ACCC Accrediation | In Progress | Ryoma | 2026-01-30 | High | 2026-02-11
102 | 1 | Dev (Phase 1) | Website Scrapping for Properties (RWAG) | Completed | Ryoma | 2026-01-30 | Med | 2026-02-11 | Website scaper completed and operating.
103 | 1 | Dev (Phase 1) | User Login Link & QR Code | Completed | Ryoma | 2026-01-30 | High | 2026-02-11
201 | 2 | Legal & Contracts | Meeting with Legal for Trademark & Agreements | In-Progress | Heman | 2026-01-21 | Med | 2026-02-11
301 | 3 | Collaboration Meetings | Schedule Meetings with Basiq | Completed | Heman | 2026-01-31 | Med | 2026-02-11
302 | 3 | Collaboration Meetings | Schedule Meetings with Realestate.com | In Progress | Heman | 2026-02-15 | Med | 2026-02-11 | Trademark and agreements pathway
303 | 3 | Collaboration Meetings | Schedule Meetings with Domain.com | Not Started | Heman | 2026-02-15 | Med | 2026-02-11
401 | 4 | Dev (Phase 2) | PM & Rental Agency Landing Page to check Tenant Ranking (By Property) | In Progress | Ryoma | 2026-02-15 | Med | 2026-02-11
402 | 4 | Dev (Phase 2) | Email Notifications for Property Manager | Completed | Ryoma | 2026-02-15 | Med | 2026-02-11 | Notifications are working, just need the actual reports with data from Basiq. Currently sending to single email address.
501 | 5 | Website Updates | Website Update (Messaging, About us, Values, Branding) | In-Progress | Heman | 2026-02-21 | High | 2026-02-11
502 | 5 | Website Updates | Domain & SSL Certificate | Not Started | Ryoma | 2026-02-21 | High | 2026-02-11
601 | 6 | Marketing & Ad Plan | Database & Contacts (Agencies) | Not Started | Akshay | 2026-02-21 | Med | 2026-02-11
602 | 6 | Marketing & Ad Plan | Brochure, AI video & Ad templates | In-Progress | Akshay | 2026-02-21 | Med | 2026-02-11
603 | 6 | Marketing & Ad Plan | CRM (Cadence Plan for Ads) | Not Started | Akshay | 2026-02-21 | Med | 2026-02-11
701 | 7 | UAT & Security | VAPT Scan & Bug Fixes | Not Started | Ryoma | 2026-02-28 | High | 2026-02-11
702 | 7 | UAT & Security | CyberSecurity & Privacy Audit & Bug Fixes | Not Started | Akshay | 2026-02-28 | Med | 2026-02-11
801 | 8 | Pilot (Go-Live) | Real Estate Agency Onboarding Kit (Link / QR & Brochure) | Not Started | Akshay | 2026-05-05 | High | 2026-02-11
901 | 9 | Product Metrics | Pilot KPI Tracking Dashboard (Onboarding Form) | Not Started | Ryoma | 2026-03-15 | Med | 2026-02-11
902 | 9 | Product Metrics | Integration & Scaling | Not Started | Ryoma | 2026-05-31 | Low | 2026-02-11

## Tech-Business Risk
Table 3
RAID ID | RAID Type | Description | Impact | Likelihood | Risk Level | Owner | Mitigation | Target Date | Status | Comments
1 | Risk | Tech Risks - Dependency on Basiq | High | High | High | Ryoma | Contract | 2026-02-15 | Pending | Contract with Basiq underway while we also have redundancies with backup service providers if necessary.
2 | Risk | Tech Risks - Scaling to handle Concurent Users | High | Med | High | Ryoma | Contract | 2026-02-15 | Pending | We are only using managed services with proven scalability. This will scale at a more economical rate than Azure or AWS until we high a very high saturation point.
3 | Risk | Compliance Risk - (CyberSecurity & Privacy) | High | Med | High | Akshay | Insurance | 2026-02-15 | Pending
4 | Risk | Business Risk - Competition | Med | Med | Med | Heman | Business & Tech Plans | 2026-02-15 | Pending
5 | Risk | Business Risk - Legal & Contracts | Med | Low | Low | Heman | Trademarks | 2026-02-15 | In-Progress

## Dev Velocity
Table 4
Date | Open | Completed | On-Hold
2025-12-19 | 5 | 0 | 0
2025-12-26 | 14 | 0 | 0
2026-01-02 | 19 | 1 | 0
2026-01-09 | 18 | 4 | 0
2026-01-16 | 18 | 4 | 0

## Decision Table
Table 5
Decision ID | Decision Required | Impact if Delayed | Required By Date | Owner | Status | Comments
1 | Onboarding Marketing Agency | Fail to Advertise & Market Product | 2026-03-01 | Raj | Completed | Onboarded Yakk

## Task Owners Table
Table 6
Owner | Role
Mannu Kala | CEO
Raj Nanalal | COO
Ryoma Ohira | CTO
Heman Germian | CCO
Priya Daga | CFO
Akshay Desai | Program Manager