## Rental IQ
Table 1 | RIQ - Milestone Schedule
ActivityID | ActivityName | StartDate | EndDate | OverallStatus | %Complete
1 | Dev (Phase 1) | 2026-01-01 | 2026-01-30 | Completed | 66%
2 | Legal & Contracts | 2026-01-14 | 2026-01-20 | Delayed | 50%
3 | Collaboration Meetings | 2026-01-21 | 2026-02-15 | Delayed | 50%
4 | Dev (Phase 2) | 2026-02-01 | 2026-02-15 | In Progress | 40%
5 | Website Updates | 2026-01-21 | 2026-02-21 | In Progress | 30%
6 | Marketing & Ad Plan | 2026-01-21 | 2026-02-21 | In Progress | 0%
7 | UAT & Security | 2026-02-01 | 2026-02-28 | Not Started | 0%
8 | Pilot (Go-Live) | 2026-03-01 | 2026-04-30 | Not Started | 0%
9 | Product Metrics | 2026-03-01 | 2026-05-31 | Not Started | 0%
10 | Production (Go-Live) | 2026-06-01 | 2026-06-01 | Not Started | 0%
Table 2 | RIQ - Activity Table |  | Update the Current Status & Comments
SubTaskID | ParentID | ActivityName | SubTaskName | Status | Owner | SubEndDate | Priority | Current Date | Comments
101 | 1 | Dev (Phase 1) | Bank Feed API Connection (Basiq) & ACCC Accrediation | In Progress | Ryoma | 2026-01-30 | High | 2026-01-28
102 | 1 | Dev (Phase 1) | Website Scrapping for Properties (RWAG) | Completed | Ryoma | 2026-01-30 | Med | 2026-01-28 | Website scaper completed and operating. | Status
103 | 1 | Dev (Phase 1) | User Login Link & QR Code | Completed | Ryoma | 2026-01-30 | High | 2026-01-28 |  | Not Started
201 | 2 | Legal & Contracts | Meeting with Legal for Trademark & Agreements | Delayed | Heman | 2026-01-21 | Med | 2026-01-28 |  | In-Progress
301 | 3 | Collaboration Meetings | Schedule Meetings with Basiq | Pending | Heman | 2026-01-31 | Med | 2026-01-28 |  | Pending
302 | 3 | Collaboration Meetings | Schedule Meetings with Realestate.com | In Progress | Heman | 2026-02-15 | Med | 2026-01-28 | Trademark and agreements pathway | Completed
303 | 3 | Collaboration Meetings | Schedule Meetings with Domain.com | Not Started | Heman | 2026-02-15 | Med | 2026-01-28
401 | 4 | Dev (Phase 2) | PM & Rental Agency Landing Page to check Tenant Ranking (By Property) | In Progress | Ryoma | 2026-02-15 | Med | 2026-01-28
402 | 4 | Dev (Phase 2) | Email Notifications for Property Manager | Completed | Ryoma | 2026-02-15 | Med | 2026-01-28 | Notifications are working, just need the actual reports with data from Basiq. Currently sending to single email address.
501 | 5 | Website Updates | Website Update (Messaging, About us, Values, Branding) | Not Started | Heman | 2026-02-21 | High | 2026-01-28
502 | 5 | Website Updates | Domain & SSL Certificate | Not Started | Ryoma | 2026-02-21 | High | 2026-01-28
601 | 6 | Marketing & Ad Plan | Database & Contacts (Agencies) | Not Started | Akshay | 2026-02-21 | Med | 2026-01-28
602 | 6 | Marketing & Ad Plan | Brochure, AI video & Ad templates | Not Started | Akshay | 2026-02-21 | Med | 2026-01-28
603 | 6 | Marketing & Ad Plan | CRM (Cadence Plan for Ads) | Not Started | Akshay | 2026-02-21 | Med | 2026-01-28
701 | 7 | UAT & Security | VAPT Scan & Bug Fixes | Not Started | Ryoma | 2026-02-28 | High | 2026-01-28
702 | 7 | UAT & Security | CyberSecurity & Privacy Audit & Bug Fixes | Not Started | Akshay | 2026-02-28 | Med | 2026-01-28
801 | 8 | Pilot (Go-Live) | Real Estate Agency Onboarding Kit (Link / QR & Brochure) | Not Started | Akshay | 2026-05-05 | High | 2026-01-28
901 | 9 | Product Metrics | Pilot KPI Tracking Dashboard | Not Started | Ryoma | 2026-03-15 | Med | 2026-01-28
902 | 9 | Product Metrics | Integration & Scaling | Not Started | Ryoma | 2026-05-31 | Low | 2026-01-28
Table 3 | RIQ - Milestone Completion |  | Ensure you update in same format (e.g., 50% should be 0.50)
ActivityID | ActivityName | Task Completion % | Milestone Weight | Completion % | Status | Overal Cummulative Completion % | Owner
1 | Dev (Phase 1) | 0.66 | 0.15 | 0.099 | In Progress | 0.099 | Ryoma
2 | Legal & Contracts | 0.5 | 0.05 | 0.025 | Delayed | 0.124 | Heman
3 | Collaboration Meetings | 0.5 | 0.05 | 0.025 | In Progress | 0.149 | Heman
4 | Dev (Phase 2) | 0.4 | 0.2 | 0.08 | In Progress | 0.229 | Ryoma
5 | Website Updates | 0.3 | 0.15 | 0.045 | Not Started | 0.274 | Akshay
6 | Marketing & Ad Plan | 0 | 0.15 | 0 | Not Started | 0.274 | Heman
7 | UAT & Security | 0 | 0.2 | 0 | Not Started | 0.274 | Akshay
8 | Pilot (Go-Live) | 0 | 0 | 0 | Not Started | 0.274
9 | Product Metrics | 0 | 0.05 | 0 | Not Started | 0.274 | Ryoma
10 | Production (Go-Live) | 0 | 0 | 0 | Not Started | 0.274

## Rental IQ 2
Table 4 | RIQ - Risk Register
Sr. No | Risks | Probablity | Impact | Status | Risk Owner | Mitigation Plan | Status | Comments
1 | Tech Risks - Dependency on Basiq | High | High | Transfer | Ryoma | Contract | Pending | Contract with Basiq underway while we also have redundancies with backup service providers if necessary.
2 | Tech Risks - Scaling to handle Concurent Users | Med | High | Transfer | Ryoma | Contract | Pending | We are only using managed services with proven scalability. This will scale at a more economical rate than Azure or AWS until we high a very high saturation point.
3 | Compliance Risk - (CyberSecurity & Privacy) | Med | High | Accept | Akshay | Insurance | Pending
4 | Business Risk - Competition | Med | Med | Accept | Heman | Business & Tech Plans | Pending
5 | Business Risk - Legal & Contracts | Low | Med | Accept | Heman | Trademarks | In-Progress
Table 5 | RIQ - Dev Tasks
Dates (Weekly) | Open | Completed
2025-12-19 | 5 | 0
2025-12-26 | 14 | 0
2026-01-02 | 19 | 1
2026-01-09 | 18 | 4
2026-01-16 | 18 | 4

## RI Insights (hidden)
Market Analytics
Sr. No | Agency Name | State | Estimated Rental Portfolio | Estimated Tenant Applications / Year | Priority Tier | Focus Areas | Onboarding Status
1 | Ray White Queensland | QLD | 120000 | 480000 | Primary | High rental turnover | Pilot (Partially)
2 | LJ Hooker Queensland | QLD | 90000 | 360000 | Primary | Strong SE QLD presence | Prospecting
3 | Ray White Property Management | NSW | 200000 | 800000 | Primary | Largest national rental portfolio | Prospecting
4 | LJ Hooker Property Management | NSW | 100000 | 400000 | Primary | Strong franchise coverage | Prospecting
5 | Harcourts Victoria | VIC | 85000 | 340000 | Primary | Tech-forward culture | Prospecting
6 | Raine & Horne | NSW | 90000 | 350000 | Secondary | High NSW density | Prospecting
7 | Barry Plant Real Estate | VIC | 70000 | 280000 | Secondary | Victoria-focused | Prospecting
8 | Acton Real Estate | WA | 35000 | 140000 | Secondary | Dominant Perth market | Prospecting
9 | Toop+Toop | SA | 25000 | 100000 | Secondary | Premium SA brand | Prospecting
10 | RE/MAX Australia (Rentals) | National | 80000 | 320000 | Secondary | Decentralised network | Prospecting
Risk Categories
Sr. No | Risks | Probablity | Impact | Status | Mitigation Plan
1 | Tech Risks - Dependency on Basiq | High | High | Transfer | Contract
2 | Tech Risks - Scaling to handle Concurent Users | Med | High | Transfer | Contract
3 | Compliance Risk - (Regulations CS & P) | Med | High | Accept | Insurance
4 | Business Risk - Competition | Med | Med | Accept | Business & Tech Plans
5 | Business Risk - Legal & Contracts | Low | Med | Accept | Trademarks
Sr. No | Platform Insights | Numbers
1 | Website Visit | 24999
2 | AI Video play | 4945
3 | Pop-up Click (Tab 1) | 6432
4 | Pop-up Click (Tab 2) | 2352
5 | Pop-up Click (Tab 3) | 1535
6 | Registration Completed | 8767
7 | Login | 7868
8 | Service Processed | 6354
9 | Report Delivered | 6333
10 | Email to sent for #Properties | 18435
Sr. No | Affordability Rating | No of users
1 | 0 - 40 | 2333
2 | 41-70 | 4545
3 | 71-100 | 1535

## AwardBook
Table 6 | AB - Milestone Schedule
Milestone ID | Milestone Name | Phase | Start Date | End Date | Status | %Complete | RAG | Owner
M1 | Development Completion | Tech | 2025-07-01 | 2026-03-15 | In-Progress | 60% | Green | Ryoma Ohira
M2 | Internal UAT | Tech | 2026-03-16 | 2026-04-01 | Not Started | 0% | Green | Ryoma Ohira
M3 | Security & Compliance | Product & Complaince | 2026-04-01 | 2026-04-30 | Not Started | 0% | Green | Akshay Desai
M4 | Pilot 1 – Single School | Pilot | 2026-05-01 | 2026-06-30 | Not Started | 0% | Green | Heman Germian
M5 | Pilot 2 – Multi School | Pilot | 2026-07-01 | 2026-09-30 | Not Started | 0% | Green | Raj Nanalal
M6 | Feature Enhancements | Product & Complaince | 2026-10-01 | 2026-11-30 | Not Started | 0% | Green | Akshay Desai
M7 | Soft Launch | Launch | 2026-12-01 | 2026-12-31 | Not Started | 0% | Green | Heman Germian
M8 | Full Launch | Launch | 2027-01-01 | 2027-01-01 | Not Started | 0% | Green | Raj Nanalal
Table 7 | AB - Activity Table |  | Update the Current Status & Comments
Task ID | Task Name | Milestone ID | Workstream | Owner | Due Date | Status | RAG | Comments | Status
T1 | Development Completion | M1 | Tech | Ryoma Ohira | 2026-03-15 | In-Progress | Green |  | Not Started
T2 | Mobile App UX Enhancements | M1 | Tech | Ryoma Ohira | 2026-03-15 | In-Progress | Green |  | In-Progress
T3 | VAPT Testing | M3 | Product & Complaince | Akshay Desai | 2026-04-30 | Not Started | Green |  | Pending
T4 | ISO 27001 Lite Controls | M3 | Product & Complaince | Akshay Desai | 2026-04-30 | Not Started | Green |  | Completed
T5 | Agency Onboarding Materials | M4 | Business | Heman Germian | 2026-06-30 | Not Started | Green
T6 | Collect Pilot Feedback | M4 | Business | Heman Germian | 2026-06-30 | Not Started | Green
T7 | Enhance Reporting Logic | M6 | Tech | Ryoma Ohira | 2026-09-30 | Not Started | Green
Table 12 | AB - Milestone Completion |  |  | Ensure you update in same format (e.g., 50% should be 0.50)
Milestone ID | Milestone Name | Milestone Completion % | Milestone Weight | Completion % | Status | Overal Cummulative Completion % | Owner
M1 | Development Completion | 0.6 | 0.3 | 0.18 | In Progress | 0.18 | Ryoma Ohira
M2 | Internal UAT | 0 | 0.1 | 0 | Not Started | 0.18 | Akshay Desai
M3 | Security & Compliance | 0 | 0.1 | 0 | Not Started | 0.18 | Akshay Desai
M4 | Pilot 1 – Single School | 0 | 0.1 | 0 | Not Started | 0.18 | Heman Germian
M5 | Pilot 2 – Multi School | 0 | 0.1 | 0 | Not Started | 0.18 | Heman Germian
M6 | Feature Enhancements | 0 | 0.2 | 0 | Not Started | 0.18 | Ryoma Ohira
M7 | Soft Launch | 0 | 0.05 | 0 | Not Started | 0.18 | Heman Germian
M8 | Full Launch | 0 | 0.05 | 0 | Not Started | 0.18

## AwardBook 2
Table 8 | AB - RAID Table | Update the Current Status & Comments
RAID ID | RAID Type | Description | Impact | Likelihood | RAG | Owner | Mitigation | Target Date | Status | Comments
R1 | Risk | Delay in pilot adoption | 4 | 3 | Amber | Heman Germian | Increase school engagement | 2026-04-30 | Open
R2 | Risk | Security findings in VAPT | 5 | 3 | Red | Akshay Desai | Early remediation | 2026-04-30 | Open
A1 | Assumption | Automated Scalability of Servers | 4 | 1 | Green | Ryoma Ohira | Additional Scalable options | 2026-07-31 | Open
D1 | Dependency | Dev Team Availability | 4 | 2 | Amber | Raj Nanalal | Additional Developers | 2026-04-30 | Open
I1 | Issue | Latency issues | 3 | 4 | Amber | Ryoma Ohira | Optimize APIs | 2026-07-31 | Open
Table 9 | AB - Decision Table | Update the Current Status & Comments | [8 empty] | Open
Decision ID | Decision Required | Impact if Delayed | Required By | Owner | Status | Comments |  |  |  |  | Closed
D001 | Approve additional security budget | Launch delay risk | 2026-04-01 | Raj Nanalal | Open | [5 empty] | Pending
D002 | Approve Additional Hiring | Development Delay & Quality Risks | 2026-04-01 | Raj Nanalal | Open
D003 | Select second pilot school | Pilot expansion | 2026-06-01 | Heman Germian | Open
Table 10 | AB - Owner Table
Owner | Role
Mannu Kala | CEO
Raj Nanalal | COO
Ryoma Ohira | CTO
Heman Germian | CCO
Priya Daga | CFO
Akshay Desai | Program Manager
Table 11 | AB - Dev Tasks
Dates | Open | Completed | Closed pull requests | Not planned | Duplicate
2025-03-31 | 0 | 1 | 0 | 0 | 0
04/30/2025 | 7 | 2 | 0 | 0 | 0
05/31/2025 | 33 | 13 | 0 | 0 | 0
06/30/2025 | 40 | 16 | 0 | 0 | 0
07/31/2025 | 41 | 29 | 0 | 1 | 0
08/31/2025 | 39 | 46 | 0 | 1 | 1
09/30/2025 | 42 | 70 | 0 | 4 | 1
10/31/2025 | 24 | 105 | 2 | 7 | 2
11/30/2025 | 32 | 135 | 2 | 7 | 2
12/31/2025 | 41 | 151 | 3 | 7 | 2
2026-01-26 | 37 | 172 | 4 | 7 | 3